## General
General Project Information
Name of Project Manager: |  | Design
Project Manager Phone: |  | Feasibility
Project Manager Email:
Project No:
Project Title:
Scope of work: (detailed)
Area/Building
Design or Construction Phase
Project Start Date
Project End Date
Name of UDM / Client:
Square footage total
Cost per Square Footage
Notes

## FM101 - Orig Budget
Form Rev: LLC 4.30.25
Facilities Management Project Budget Authorization
| To: |  | 0 |  |  |  |  | Date:
Client
| From: |  | 0 |  |  |  |  | Phone: | 0
|  |  | 0 |  |  |  |  | E-mail: | 0
| Project Number: |  | 0 |  |  |  | Project Title: | 0
Project costs are to be encumbered against (F/CC):
| Bldg/Facility Name(s): |  |  |  |  | Room(s)# | [5 empty] | Division/Area:
As per your request, a feasibility study has been completed for the following scope of work:
0
| Check all that apply: |  |  |  | Emergency work |  |  |  | Planned Capital Repair/Improvement
[5 empty] | Planned Renovation |  |  |  | Project will increase Energy and Utilities
[5 empty] | Project will increase FM Labor |  |  |  | Project will decrease FM Labor
[5 empty] | Improves accessibility |  |  |  | Estimated to be over $40k (capitalizable)
ESTIMATE
| The total cost of the project is |  |  | 0 |  |  | including contigency: |  |  |  | 0
This estimate applies if this project is implemented before:
Further details about the budget are included on subsequent page.
Put notes about budget in here, e.g. overall budget for project
SCHEDULE
| We estimate that the project is to start |  |  |  |  | 0 |  |  | and finish around
0
| 0 |  | based on approval within 10 days. Afterward, schedule and budget subject to change.
Put information about milestones and schedule specifics in here
This project is approved for : |  |  |  | Design | [5 empty] | Construction
| Approved By | [5 empty] | Print: |  |  |  |  | Date: __________ | Date: __________
Client
| Approved By | [5 empty] | Print: |  |  |  |  | Date: __________ | Date: __________
Chair or Director
| Approved By | [5 empty] | Print: |  |  |  |  | Date: __________ | Date: __________
Dean/Sr. Director, etc.
| Approved By | [5 empty] | Print: |  |  |  |  | Date: __________ | Date: __________
VP or AVP of Client Division
| Approved By | [5 empty] | Print: |  |  |  |  | Date: __________ | Date: __________
VP or AVP of Business and Finance (required if above Div. VP's signature authority level)
Note: All funding must follow limits set for by the BOT Authority to Sign; The project is officially initiated after funding approval is processed.
This section is for FM Business Operations (269) 387-8532:
63 No Yes | [6 empty] | Fee Waiver
___ Capitalized ___ Non-Capitalized | [6 empty] | PM Email: | 0
Definition of Deliverables and Understanding of Services
The deliverables of the project are:
|  | O | Construction documents (drawing & specifications)
|  | O | Proposed project duration
|  | O | Construction Budget
Put additional understanding of service in here
BUDGET SUMMARY
Design and Feasibility Phase Budget
|  |  | 100 - Study | [6 empty] | 0
|  |  | 200 - Programming | [6 empty] | 0
|  |  | 300 - Schematic Design | [6 empty] | 0
|  |  | 400 - Design Documents | [6 empty] | 0
|  |  | 500 - Construction Documents | [6 empty] | 0
|  |  | 600 - Pre-Construction | [6 empty] | 0
|  |  | 700 - Construction | [6 empty] | 0
|  |  | Design Phase Contingency | [6 empty] | 0
|  | TOTAL DESIGN BUDGET | [7 empty] | 0
Construction Phase Budget
|  |  | Division 1 - General Requirements | [6 empty] | 0
|  |  | Division 2 - Site Conditions | [6 empty] | 0
|  |  | Division 3 - Concrete | [6 empty] | 0
|  |  | Division 4 - Masonry | [6 empty] | 0
|  |  | Division 5 - Metals | [6 empty] | 0
|  |  | Division 6 - Wood/Plastics | [6 empty] | 0
|  |  | Division 7 - Thermal/Moisture Protection | [6 empty] | 0
|  |  | Division 8 - Openings | [6 empty] | 0
|  |  | Division 9 - Finishes | [6 empty] | 0
|  |  | Division 10 - Specialites | [6 empty] | 0
|  |  | Division 11 - Equipment | [6 empty] | 0
|  |  | Division 12 - Furnishings | [6 empty] | 0
|  |  | Division 13 - Special Construction | [6 empty] | 0
|  |  | Division 14 - Conveying Systems | [6 empty] | 0
|  |  | Division 21 - Fire Suppression | [6 empty] | 0
|  |  | Division 22 - Plumbing | [6 empty] | 0
|  |  | Division 23 - HVAC | [6 empty] | 0
|  |  | Division 25 - Integrated Automation | [6 empty] | 0
|  |  | Division 26 - Electrical | [6 empty] | 0
|  |  | Division 27 - Communication | [6 empty] | 0
|  |  | Division 28 - Electronic Safety/Security | [6 empty] | 0
|  |  | Division 31 - Earthwork | [6 empty] | 0
|  |  | Division 32 - Exterior Improvements | [6 empty] | 0
|  |  | Division 33 - Utilities | [6 empty] | 0
|  |  | Division 34 - Transportation | [6 empty] | 0
|  |  | Contruction Phase Contingency | [6 empty] | 0
|  |  | Facilities Management Fees | [6 empty] | 0
|  | TOTAL CONSTRUCTION BUDGET | [7 empty] | 0

## FM102 - Budget Change
Form Rev: LLC 4.30.25
Facilities Management Project Budget Change Authorization
| To: | 0 |  | Change Authorization #:
| From: | 0 |  | Phone: | 0
|  | Project Manager |  | E-mail: | 0
| Date: | 2025-04-30
|  | Project Number: | 0
|  | Project Title: | 0
Project costs are to be encumbered against (F/CC):
|  | New Project Scope: | Summarize changed scope of work & indicate schedule changes if applicable
|  |  |  | Current Budget: |  |  | 0
|  | Scope Changes: | 1) |  | $
|  |  | 2) |  | $
|  |  | 3) |  | $
|  |  | 4) |  | $
|  |  | 5) |  | $
|  |  | 6) |  | $
| Total Scope changes |  |  |  | $ | 0 | 0
| New Total Project Budget |  |  |  | $ | 0 | 0
| Approved By |  |  |  | Print: |  |  |  | Date: __________ | Date: __________
Client
| Approved By |  |  |  | Print: |  |  |  | Date: __________ | Date: __________
Chair or Director
| Approved By |  |  |  | Print: |  |  |  | Date: __________ | Date: __________
Dean/Sr. Director, etc.
| Approved By |  |  |  | Print: |  |  |  | Date: __________ | Date: __________
VP or AVP of Client Division
| Approved By |  |  |  | Print: |  |  |  | Date: __________ | Date: __________
VP or AVP of Business and Finance (required if above Div. VP's signature authority level)
Note: All funding must follow limits set for by the BOT Authority to Sign
This section for use by Facilities Management Business Operations (269)387-8532
63 No Yes
___ Capitalized ___ Non-Capitalized |  |  |  | PM Email: | 0

## FM103 - Services Estimate
Facilities Management Services Estimate-
Project Title: | 0 |  |  | Project number: | 0
Area: | 0 |  |  | Sqft: | 0
Project Manager: | 0 |  |  | Date:
Budget
D (Design) and C (Construction) Division |  | Quantity | Unit Cost | Estimate | Description | Actuals
100 - Study | Total |  |  | 0
Direct Payroll
| Consultants |  |  | 0
| Reimbursable |  |  | 0
200 - Programming | Total |  |  | 0
| Direct Payroll |  |  | 0
| Consultants |  |  | 0
| Reimbursable |  |  | 0
300 - Schematic Design | Total |  |  | 0
| Direct Payroll |  |  | 0
| Consultants |  |  | 0
| Reimbursable |  |  | 0
400 - Design Documents | Total |  |  | 0
| Direct Payroll |  |  | 0
| Consultants |  |  | 0
| Reimbursable |  |  | 0
500 - Construction Documents | Total |  |  | 0
| Direct Payroll |  |  | 0
| Consultants |  |  | 0
| Reimbursable |  |  | 0
600 - Pre-Construction | Total |  |  | 0
| Direct Payroll |  |  | 0
| Consultants |  |  | 0
| Reimbursable |  |  | 0
700 - Construction | Total |  |  | 0
| Direct Payroll |  |  | 0
| Consultants |  |  | 0
| Reimbursable |  |  | 0
Design Phase Contingency |  | 5% |  | 0
| Total Design Budget |  |  | 0
Division 1 - General Requirements | Total |  |  | 0
| Testing |  |  | 0
| Inspection |  |  | 0
| QC |  |  | 0
0
Division 2 - Site Conditions | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 3 - Concrete | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 4 - Masonry | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 5 - Metals | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 6 - Wood/Plastics | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 7 - Thermal/Moisture Protection | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
Waterproofing |  |  |  | 0
Insulation |  |  |  | 0
Roofing |  |  |  | 0
Fireproofing |  |  |  | 0
Division 8 - Openings | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 9 - Finishes | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 10 - Specialites | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 11 - Equipment | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 12 - Furnishings | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 13 - Special Construction | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 14 - Conveying Systems | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 21 - Fire Suppression | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 22 - Plumbing | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 23 - HVAC | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 25 - Integrated Automation | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 26 - Electrical | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 27 - Communication | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 28 - Electronic Safety/Security | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 31 - Earthwork | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 32 - Exterior Improvements | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 33 - Utilities | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 34 - Transportation | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Contruction Phase Contingency | Total |  |  | 0
| Owner | 5% | % | 0
| Construction | 5% | % | 0
TOTAL DESIGN and CONSTRUCTION ESTIMATE WITHOUT FEES |  |  |  | 0
CALCULATED FEES |  |  |  | 0
TOTAL DESIGN and CONSTRUCTION COST |  |  |  | 0

## Cost Tracking_STV
Approved Budget (XXXX) | [approved $$$ amount] |  | Form Rev: LLC 4.30.25
Description | Estimated Budget | Projected Final Budget | Committed to Date | Available Balance
Construction Cost
CM Fees
Bond Fees
Total Approved Change Orders
Preliminary Change Orders
Construction Cost | 0 | 0 | 0 | 0
Cabling & Infrastructure
Media & Equipment
Telecom | 0 | 0 | 0 | 0
Owner Furnished Equipment
Furniture
Owner Finished Material and Equipment | 0 | 0 | 0 | 0
Construction Testing
Moving
Temporary Facilities
Agency Approval Fees
Shops
Environmental
Misc., Printing & Mailing
Testing & Misc. Subtotal | 0 | 0 | 0 | 0
A/E Fees
Owner Representative
Commissioning
Professional Fees | 0 | 0 | 0 | 0
Subtotal | 0 | 0 | 0 | 0
Contingency % | #VALUE! | #VALUE!
Contingency | #VALUE! | #VALUE!
Project Total | [approved $$$ amount] | [approved $$$ amount]

## Change Orders_STV
Description of change | WMU PCE # Not in Contract | WMU Change Order | Estimated cost of change | Total Approved Change Orders | Reason for Change
|  |  | 0 | 0
Reason Code
RC- Requested change
DE/O- Design Error or Ommision
UC- Unforseen Condition
CE - Coordination Error
X- Other |  |  |  |  | Form Rev: LLC 4.30.25

## Old Change Authorization
Facilities Management Services Estimate-
Project Title: | 0 |  |  | Project number: | 0
Area: | 0 |  |  | Sqft: | 0
Project Manager: | 0 |  |  | Date:
Budget
D (Design) and C (Construction) Division |  | Quantity | Unit Cost | Estimate | Description | Actuals
100 - Study | Total |  |  | 0
| Direct Payroll |  |  | 0
| Consultants |  |  | 0
| Reimbursable |  |  | 0
200 - Programming | Total |  |  | 0
| Direct Payroll |  |  | 0
| Consultants |  |  | 0
| Reimbursable |  |  | 0
300 - Schematic Design | Total |  |  | 0
| Direct Payroll |  |  | 0
| Consultants |  |  | 0
| Reimbursable |  |  | 0
400 - Design Documents | Total |  |  | 0
| Direct Payroll |  |  | 0
| Consultants |  |  | 0
| Reimbursable |  |  | 0
500 - Construction Documents | Total |  |  | 0
| Direct Payroll |  |  | 0
| Consultants |  |  | 0
| Reimbursable |  |  | 0
600 - Pre-Construction | Total |  |  | 0
| Direct Payroll |  |  | 0
| Consultants |  |  | 0
| Reimbursable |  |  | 0
700 - Construction | Total |  |  | 0
| Direct Payroll |  |  | 0
| Consultants |  |  | 0
| Reimbursable |  |  | 0
Design Phase Contingency |  | 5% | % | 0
| Total Design Budget |  |  | 0
Division 1 - General Requirements | Total |  |  | 0
| Testing |  |  | 0
| Inspection |  |  | 0
| QC |  |  | 0
0
Division 2 - Site Conditions | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 3 - Concrete | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 4 - Masonry | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 5 - Metals | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 6 - Wood/Plastics | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 7 - Thermal/Moisture Protection | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
Waterproofing |  |  |  | 0
Insulation |  |  |  | 0
Roofing |  |  |  | 0
Fireproofing |  |  |  | 0
Division 8 - Openings | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 9 - Finishes | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 10 - Specialites | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 11 - Equipment | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 12 - Furnishings | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 13 - Special Construction | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 14 - Conveying Systems | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 21 - Fire Suppression | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 22 - Plumbing | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 23 - HVAC | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 25 - Integrated Automation | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 26 - Electrical | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 27 - Communication | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 28 - Electronic Safety/Security | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 31 - Earthwork | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 32 - Exterior Improvements | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 33 - Utilities | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Division 34 - Transportation | Total |  |  | 0
| Labor |  |  | 0
0
0
0
| Material |  |  | 0
0
0
0
0
Contruction Phase Contingency | Total |  |  | 0
| Owner | 5% | % | 0
| Construction | 5% | % | 0
TOTAL DESIGN and CONSTRUCTION ESTIMATE WITHOUT FEES |  |  |  | 0
CALCULATED FEES |  |  |  | 0
TOTAL DESIGN and CONSTRUCTION COST |  |  |  | 0

## Old Cost Estimate Tool
Facilities Management Cost Estimate
Project Title:
Project Manager:
Project number: |  |  | Date:
Scope of Work:
Division | Quantity | Unit Cost | Estimate | Actual
WMU Electrical Labor |  |  | 0
WMU Structural Labor |  |  | 0
WMU Painting Labor |  |  | 0
WMU Plumbing Labor |  |  | 0
WMU Labor-Other |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Asbestos |  |  | 0
Fire alarm/suppression |  |  | 0
Security |  |  | 0
Sub total WMU labor |  |  | 0 | 0
Sub total other |  |  | 0 | 0
General Conditions % |  |  | 0
Contingency % |  |  | 0
Subtotal |  |  | 0 | 0
Total less contingency |  |  | 0 | 0
Total for Prof fee calculation |  |  | 0 | 0
Professional Fees | No |  | 0 | 0
Design fees | No |  | 0 | 0
Estimated total project budget: |  |  | 0
Actual total project: | FM-103 |  |  | 0